## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ST-DW-0077 |  |  |  |  | EPC Contractor Tr. No. : BK-HD-PEDCO-T-2395 |  |  | Transmital Date:9/30/2023
Document Title: Foundation Drawing For CCTV Control Room- Binak DU |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0073-ST-T-2395 |  |  | Transmital Date:9/30/2023
[5 empty] | CRS No:NISOC-CRS- BK-GCS-PEDCO-120-ST-DW-0077_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 1402-2294-312579 | 1402/08/07 | با توجه به مدرک ضوابط طراحی مقاومت 15 مگاپاسکال در نظر گرفته شده است
2 |  |  | 1402-2294-312579 | 1402/08/07 | مختصات براساس صورتجلسه مورخ 1402/8/15 در نقشه ها درج گردیده است
3 |  |  | 1402-2294-312579 | 1402/08/07 | با توجه به ارتفاع 60 سانتیمتری نیازی به میلگرد مذکور نمی باشد
4 |  |  | 1402-2294-312579 | 1402/08/07 | طول همپوشانی میلگردها اضافه گردید
5 |  |  | 1402-2294-312579 | 1402/08/07 | نوت شماره 6 نقشه جهت کاور درج گردیده است
6 |  |  | 1402-2294-312579 | 1402/08/07 | نت شماره 9 جهت تراکم درج گردیده است
7 |  |  | 1402-2294-312579 | 1402/08/07 | نت شماره 10 به نقشه اضافه گردید
8 |  |  | 1402-2294-312579 | 1402/08/07 | لیسوفر به نقشه اضافه گردید
9 |  |  | 1402-2294-312579 | 1402/08/07 | محل مورد نظر به نقشه اضافه گردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: