## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-PI-SP-0001_D04 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2515 |  |  | Transmital Date: 12/2/2023
Document Title: Piping Material Specification |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PI-TR-2515 |  |  | Transmital Date: 12/2/2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PI-SP-0001_D04 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | همانگونه که در نامه 02/2294/342197 اعلام گردید،تمامی استانداردهایBS با استانداردمتناظر API میبایست جایگزین شوند. |  | 1402/2294/432166 | 1402/10/23 | نقطه نظر کارفرمای محترم اعمال گردید.
2 | رعایت الزامات بند6-7 مدرک سطح بازرسی کالا و تجهیزات با در نظر گرفتن MTO پروژه الزامی است. در صورت عدم تامین الزامات این بند می بایست ساخت کالا مدنظر قرار گیرد. |  | 1402/2294/432166 | 1402/10/23 | این موضوع در MR و TBEمد نظر قرار میگیرد.
3 | با توجه به بند فوق در خصوص تامین/خرید کالا در زمان ارائه مدارک مهندسی خرید اظهار نظر خواهد شد. |  | 1402/2294/432166 | 1402/10/23 | در زمان تهیه TBE تایید کارفرمای محترم در این خصوص اخذ می گردد.
4 | تعیین مشخصات دقیق کالا در داده برگهای مربوطه در مرحله مهندسی خرید کالاو با در نظر گرفتن نظرات سازندگان صورت خواهد پذیرفت. |  | 1402/2294/432166 | 1402/10/23 | در زمان تهیه TBE تایید کارفرمای محترم در این خصوص اخذ می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: