## Sheet 1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GNRAL-PEDCO-220-SA-PY-0001_D02 |  |  |  |  | EPC Contractor Tr. No : BK-HD-PEDCO-T-0908 |  |  | Transmital Date:08/May/2022
Document Title: Safety & Fire Fighting Equipment Location Layout - NISOC Residential Building |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-SF-0908 |  |  | Transmital Date:08/May/2022
[5 empty] | CRS No:NISOC-CRS-BK-GNRAL-PEDCO-220-SA-PY-0001_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در Sheet 1 آلام دیداری و شنیداری و شستی اعلان حریق شماره 4 در نقشه نمایش داده شود. |  | 1401/2294/94376 | 1401/03/18 | متعاقبا در مدارکی مربوطه ای که درآینده تولید خواهد شد، اعمال خواهد گردید.
2 | لازم است جهت هر یک از اتاق های ساختمان ها (بغیر از سرویس های بهداشتی)، دتکتور مناسب به تعداد کافی نصب گردد. |  | 1401/2294/94377 | 1401/03/18 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: