## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-MR-0008 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2263 |  |  | Transmital Date:7/24/2023
Document Title: PMR For Chemical Injection Packages |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-ME-TR-2263 |  |  | Transmital Date:7/24/2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-ME-MR-0008_D02 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | همانگونه که در نامه های شماره 01/2294/327164 و 01/2294/249425 بیان گردیده است، ساختار کلی مدارک مورد تایید بوده و لیکن ارسال نسخه بعدی مدارک فوق منوط به نهایی سازی کلیه مدارم مرتبط مهندسی و درج نسخه تایید شده (AFC) خواهد بود. لذا صدور نسخه جدید مدرک در حالی که مدارک پیشنیاز به طور کامل نهایی نشده است توجیه پذیر نبوده و تنها سبب مکاتبات مضاعف خواهد بود. |  | 1402-2294-203855 | 1402/05/24 | مدرک MR پکیج خوردگی به همراه آخرین ویرایش مدارک مرجع (ATTACHMENT#1) خدمت کارفرمای محترم ارسال می گردد.با توجه به اینکه مدارک پیوست تقریباً نهایی شده است لذا خواهشمند است جهت تسریع در امور خرید بررسی مدرک مذکور در دستور کار آن کارفرمای محترم قرار گیرد.
2 | با توجه به قطع همکاری آقای آدینه با پیمانکار، ارسال مدارک به نام ایشان صحیج نبوده و ضروری است سوابق نفرات جدید و چارت مهندسی پروژه، مجددا ارسال و بررسی گردد. |  | 1402-2294-203855 | 1402/05/24 | سوابق نفرات و چارت مهندسی متعاقبا ارسال خواهد شد.
3 |  |  |  |  | خواهشمند است نقطه شرکت محترم پترو ایران مشاهده گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature | H.Naserizadeh |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: