## Sheet1
| N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
| Document No: BK-GCS-PEDCO-120-ME-MR-0008 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2263 |  |  | Transmital Date: 7/24/2023
| Document Title: PMR For Chemical Injection Packages |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-ME-TR-2263 |  |  | Transmital Date: 7/24/2023
[6 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-ME-MR-0008_D02 |  |  | CRS Status:
|  | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
| 1 | No Comment. |  | BK-SUR-ENG-MEC-01-06099 | 2022-11-06 | مدرک MRپکیج خوردگی به همراه آخرین ویرایش مدارک مرجع ATTACHMENT#1خدمت کارفرمای محترم ارسال می گردد.همچنین از کارفرمای محترم خواهشمند است فایل پیوست اکسل،ملاحظه گردد.
QC Comments :
| 2 | عبارت QA organization به QA/QC Organization تغيير يابد. |  | BK-SUR-ENG-MEC-02-08234 | 2023-08-07 | نقطه نظر کارفرمای محترم مد نظر قرار گرفته شده است
| 3 | در رديف 5.1.8 شماره مدرك بصورت شماره مدرك بصورت صحيح E&C-QC-SP-1 وارد گردد. |  | BK-SUR-ENG-MEC-02-08234 | 2023-08-07 | نقطه نظر کارفرمای محترم مد نظر قرار گرفته شده است
| 4 | جهت يكسان سازي در كليه مدارك MR پروژه، نگارش توضيحات بند6 مطابق ذيل انجام گردد. |  | BK-SUR-ENG-MEC-02-08234 | 2023-08-07 | نقطه نظر کارفرمای محترم مد نظر قرار گرفته شده است
The equipment shall be inspected and tested in accordance with the Inspection &Test plan (ITP) issued by the vendor and approved by the CLIENT and EPC/EPD CONTRACTOR(GC) before the award of the order . The Inspection & Test plan (ITP ) shall be at least according to the Commodity Procurement and Manufacturing Inspection Instruction ( Docs .Nos. ICE-EID-MI-SP01-Rev01) , Inspection Level of Commodity and Equipment ( Docs .Nos. ICE-EID-MI-SP02-Rev01) and Data Sheets. The vendor shall in any case conduct all the tests required by contractual documents, specifications, codes and standards, manufacturer standard quality system and keep the relevant documentation. All required manufacturing and function test/inspection also Factory Acceptance Test /Site Acceptance Test and Quality Assurance requirements shall be considered in vendor responsibility as per project specification.
| 5 | لغت ''Purchaser" بايستي در قسمت General Definition تعريف گردد. |  | BK-SUR-ENG-MEC-02-08234 | 2023-08-07 | نقطه نظر کارفرمای محترم مد نظر قرار گرفته شده است
| 6 | جهت يكسان سازي، لغت Supplier در متون به Vendor تغيير يابد. |  | BK-SUR-ENG-MEC-02-08234 | 2023-08-07 | نقطه نظر کارفرمای محترم مد نظر قرار گرفته شده است
| 7 | در بند 11( Price Breakdown )شماره مدرك بصورت صحيح''E&C-QC-SP-1" آورده شود. |  | BK-SUR-ENG-MEC-02-08234 | 2023-08-07 | نقطه نظر کارفرمای محترم مد نظر قرار گرفته شده است
| 8 | در جدول Attachment 1(List of Reference/Applicable Documents): در رديف General ، شماره مدرك بصورت صحيح E&C-QC-SP-1 ذكر گردد( با ذكر rev ) |  | BK-SUR-ENG-MEC-02-08234 | 2023-08-07 | نقطه نظر کارفرمای محترم مد نظر قرار گرفته شده است
| 9 | در جدول Attachments 2(Vendor Documents Minimum Requirements): 1-در رديف 1، عبارت "See Attachment 2" حذف گردد. 2- Painting Operator Qualification Record اضافه گردد. 3- SAT Procedure اضافه گردد. 4- عبارت "List of Documents will be Finalized in Vendor Document Index and Schedule" درانتهاي جدول آورده شود. |  | BK-SUR-ENG-MEC-02-08234 | 2023-08-07 | نقطه نظر کارفرمای محترم مد نظر قرار گرفته شده است
`
| Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
| Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
|  | Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
|  | Date: |  |  |  |  | Date: