## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-CN-0006 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2442 |  |  | Transmital Date: 10/17/2023
Document Title: Calculation Note For Control Valve Sizing |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-T-2442 |  |  | Transmital Date: 10/17/2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-CN-0006_D07 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | پیشبرد فعالیت وابسته جهت گام بعدی بلامانع می باشد. بدیهی است محسبات شیرآلات کنترل پس از انتخاب سازنده مربوطه می بایست جهت بررسی این امور ارسال گردد هر گونه تغییر در هرمقطعی از پروژه در دیگر مدارک به نحوه مقتضی در این مدرک و برعکس اعمال گردد.(مستقل از تقدم و تاخر) |  | 1402-2294-389670 | 1402/09/25 | مورد تایید است لازم به ذکر است بازگشت به کامنت کارفرمای محترم در خصوص تغییر سایز شیر کنترلی PCV-2135A/B/C طی نامه شماره 1402-2294-338086 مورخ 1402/08/23 مدرک مذکور بروز رسانی گرید. و همچنین میزان OPENING شیرها مورد بازنگری مجدد قرار گرفت
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: