## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-NISOC-120-IN-LD-0002 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2399 |  |  | Transmital Date: 10/1/2023
Document Title: ESD Logic Diagram |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-2399 |  |  | Transmital Date: 10/1/2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-NISOC-120-IN-LD-0002_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | آیا منظور از Voating 2oo3 ، همان 2 از 3 می باشد؟ |  | 1402-2294-315363 | 1402/08/09 | منظور از Voting 2oo3 ، یا Two-out-of-three voting همان رای گیری 2 از 3 می باشد.
2 | لازم است مدرک پس از نهایی سازی مدرک CAUSE & EFFECT سیستم F&G و نحوه تعامل آن با سیستم ESD مورد بازنگری قرار گیرد و در صورت نیاز ویرایش گردد. |  | 1402-2294-315363 | 1402/08/09 | ملاحظه شد.
* | بدیهی است که مسئولیت تطابق مدارک اصلاحی با نقطه نظرات کارفرما و همچنین صحت و کفایت محتوای کلیه مدارک ارسالی مطابق شرح خدمات و استانداردهای تصریح شده در اسناد مناقصه، استانداردهای IPS و دیگر مدارک پروژه بر عهده پیمانکار بوده و نقطه نظرات کارفرما رافع مسئولیت پیمانکار نمی باشد. |  | 1402-2294-315363 | 1402/08/09 | ملاحظه شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: