## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GNRAL-PEDCO-000-PI-SP-0008_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1607 |  |  | Transmital Date: 26-Nov.-2022
Document Title: Specification For Material Requirements in Sour service |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PI-TR-1607 |  |  | Transmital Date:26-Nov.-2022
[5 empty] | CRS No:PEDCO-CRS-BK-GNRAL-PEDCO-000-PI-SP-0008_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نظرات بصورت مارك شده در مدرك به پيوست ارسال مي گردد. |  | BK-SUR-ENG-PIP-00-01462 | 2021-09-05 | در همان مدرک پاسخ داده شد.
2 | ويرايش مدرك IPS-M-PI-190 (3) در تمام مدرك اعمال گردد. تطابق با Annex H استاندارد API 5L براي لوله هاي سرويس ترش ذكر گردد. |  | BK-SUR-ENG-PIP-01-06344 | 05-Dec.-2022 | به استحضار می رساند Annex H صرفا برای خطوط لوله استفاده می شود. در این پروژه لوله A106 استفاده می شود.
3 | در صفحه 11 جمله Unless otherwise stated in specification, No HIC Testing is required on seamless pipe & fitting قابل قبول نيست و در اين خصوص بايستي به Annex H استاندارد API 5L اشاره گردد. تست HIC در صورتي براي لوله هاي seamless مورد نياز نيست كه تركيب شيميايي مذكور در Annex H رعايت گردد. |  | BK-SUR-ENG-PIP-01-06344 | 05-Dec.-2022 | به استحضار می رساند Annex H صرفا برای خطوط لوله استفاده می شودکه مطابق IPS تست های خط لوله انجام می شود.. در داخل سایت متریال A106 استفاده می شود.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri J.mousazadeh | Signature |  |  |  | Clarified By: S.Faramarzpour | Signature
| Date:05-Dec-2022 |  |  |  |  | Date:05-Dec-2022