## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PI-DT-0002 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2354 |  |  | Transmital Date: 9/11/2023
Document Title: Data Sheets For Manual valves |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PI-TR-2354 |  |  | Transmital Date: 9/11/2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PI-DT-0002_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | استاندارد های طراحی BS با استاندارد متناظر خود جایگزین شوند. |  | 1402-2294-333012 | 1402/08/20 | نقطه نظرکارفرمای محترم اعمال گردید.
2 | جنس شیرالات میبایست با استفاده از استاندارد IPS-E-PI-221 و برای هر کلاس شیراآلات اصلاح شود. |  | 1402-2294-333012 | 1402/08/20 | جنس شیراآلات مطابق با مدرک PMS بوده و اساس IPSنیز می باشد.
3 | دلیل اینکه کلاس AN04لزوم مطابقت با الزامات NACE MR0175 را ندارد توضیح داده شود. |  | 1402-2294-333012 | 1402/08/20 | كلاس AN04 همانگونه كه در مدرك PMS مشخص گرديده است شامل سرويس هاي Plant air, Lean GLYCOL, Fire Water مي باشد كه اين سرويس ها غير ترش بوده و نيازي به تطابق با الزامات NACE ندارند.
4 | پذیرش حد مجاز خوردگی اعلام شده پس از نهایی سازی مدرک مطالعات خوردگی قابل بررسی می باشد. |  | 1402-2294-333012 | 1402/08/20 | مدرک مورد نظر ارسال و توسط کارفرمای محترم تایید شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: