## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-PPL-PEDCO-320-PL-DT-0002 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1203 |  |  | Transmital Date: 7/26/2022
Document Title: Data Sheets For Barred Tee |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PL-TR-1203 |  |  | Transmital Date: 7/26/2022
[5 empty] | CRS No:NISOC-CRS-BK-PPL-PEDCO-320-PL-DT-0002_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به الزامات استاندارد NACE MR0175 میبایست سختی سنجی و عملیات حرارتی برای جوش ها در نظر گرفته شود. |  | 1401-2294-216165 | 1401/06/17 | نقطه نظر کارفرمای محترم اعمال گردید.
2 | در خصوص لزوم عملیات حرارتی برای ASTM A234 WPB مطابق بند 7.2 استاندارد مذکور عمل گردد. |  | 1401-2294-216165 | 1401/06/17 | الزامات مطرح شده در این بند توسط سازنده می بایست رعایت گردد و موردی به عهده خریدار نگذاشته که در این مرحله انتخاب گردد.
3 | عدد سختی برای متریال ASTM A234WPB مطابق استاندارد NACE MR0175 بندA2.1.3.4 حداکثر 197HBW در نظر گرفته شود. |  | 1401-2294-216165 | 1401/06/17 | نقطه نظر کارفرمای محترم اعمال گردید.
4 | مبنای فشار طراحی ذکر گردد. |  | 1401-2294-216165 | 1401/06/17 | بر اساس P&ID می باشد.
5 | با توجه به عدم تایید محاسبات ضخامت و نهایی نشدن مدرک PMS ضخامت های مندرج قابل استناد نبوده و میبایست اصلاح گردد. |  | 1401-2294-216165 | 1401/06/17 | مدرک PMS ارسال و توسط کارفرمای محترم تایید شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: