## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-DT-0008_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1434 |  |  | Transmital Date: 9/24/2022
Document Title: Data Sheets For Level Switch |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1434 |  |  | Transmital Date:9/24/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-IN-DT-0008_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مطابق بند 13 شرايط عمومي پيمان في مابين و با توجه به مسئوليتهاي كامل مالي/قراردادي پيمانكار, مسئوليت بروز هرگونه اشتباه و تناقض, كمبود اسناد و مدارك فني و اطلاعات تهيه شده توسط پيمانكار, اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد, به عهده پيمانكار فرعي (هيرگان) مي باشد. |  | BK-SUR-ENG-INS-01-05885 | 2022-10-10 | ملاحظه گردید |  |  | بسته شد
2 | دانسیته سیال، اصلاح گردد. |  | BK-SUR-ENG-INS-01-05885 | 2022-10-10 | اصلاح گردید |  |  | بسته شد
3 | مبنای در نظر گرفتن فشار 7 بار به عنوان فشار طراحی، مشخص گردد. |  | BK-SUR-ENG-INS-01-05885 | 2022-10-10 | اصلاح گردید |  |  | بسته شد
4 | سايز كانكشن درج شده در اين مدرك با سايز كانكشن در mechanical data sheet مغايرت دارد. موارد اصلاح و همسان سازي بين مدارك در نظر گرفته شود. |  | BK-SUR-ENG-INS-01-05885 | 2022-10-10 | سایز کانکشن 2 اینچ فلنجی با rating 300# در نظر گرفته خواهد شد. |  |  | بسته شد
5 | ويرايش مدرك P&ID ذكر گردد. |  | BK-SUR-ENG-INS-01-05885 | 2022-10-10 | اصلاح گردید |  |  | بسته شد
D02
1 | در این مقطع نقطه نظر خاصی مطرح نمی باشد |  | BK-SUR-ENG-INS-02-08487 | 2023-09-19 | ملاحظه گردید
1 | ترانسمیتال عودت داده شده است. |  | BK-SUR-ENG-INS-02-08487 | 2023-09-19 | ملاحظه گردید
D02(Replace 1)
1 | در این مقطع نقطه نظر خاصی مطرح نمی باشد |  | BK-SUR-ENG-INS-02-08598 | 2023-10-14 | ملاحظه گردید
1 | ترانسمیتال عودت داده شده است. |  | BK-SUR-ENG-INS-02-08598 | 2023-10-14 | مدرک مجدد ارسال شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 14 Oct 2023 |  |  |  |  | Date: