## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-AR-DW-0008 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2537 |  |  | Transmital Date:1/29/2024
Architectural Drawing For CCTV Control Room- Binak GCS |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-AR-T-2537 |  |  | Transmital Date:1/29/2024
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-AR-DW-0008_D05 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | عطف به نامه شماره 269001 مورخ 1402/07/09 مدرک OVERALL CABLE ROUTE در فهرست مراجع درج گردد. |  | 1402-2294-467628 | 1402/11/14 | اعمال گردید.
2 | جانمایی ساختمان میبایست مطابق با صورتجلسه مورخ 1402/08/15، اصلاح گردد و مختصات در نوت نقشه درج گردد.(درب ورودی ساختمان به سمت شرق و نردبان به سمت غرب باشد.) |  | 1402-2294-467628 | 1402/11/14 | اعمال گردید.
3 | به آگاهی میرساند نظر به اینکه مطابق ماده 13 شرایط عمومی پیمان تصویب اسناد و مدارک فنی، مهندسی و طراحی از سوی کارفرما، از هیچیک از مسئولیت ها و تعهدات قراردادی پیمانکار نمی کاهد، در صورت رفع موارد فوق صدور ویرایش AFC برای این مدرک بلامانع است. |  | 1402-2294-467628 | 1402/11/14 | موارد فوق اصلاح و مدرک AFC ارسال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: