## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W046S-PEDCO-110-GT-RT-0001 |  |  |  |  | EPC Contractor Tr. No.:BK-HD-PEDCO-T-2499 |  |  | Transmital Date:11/20/2023
Document Title: Geotechnical Investigation Report - W046S |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-GT-T-2499 |  |  | Transmital Date:11/20/2023
[5 empty] | CRS No:NISOC-CRS-BK-W046S-PEDCO-110-GT-RT-0001_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | طبق شرح کار تحت الارض بینک در چاه محل W046S تعیین عمق خاک نباتی جز حداقل مواردی است که میبایست در گزارش ژنوتکنیک مورد بررسی قرار گیرد. |  | 1402/2294/467627 | 1402/11/14 | "با توجه به اینکه گمانه 3 متری موردنظر در مسیر فلولاین و در کریدور خطوط جریانی موجود بوده و ظرفیت باربری خاصی برای آن نیاز نمیباشد، لزومی به حفر گمانه عمیق تر برای آن نمی باشد، لذا متعاقب مذاکرات تلفنی و توافق صورت گرفته با سرپرست سیویل مجموعه مجری کارفرمای اصلی محترم پروژه، مدرک با وضعیت AFC ارسال می گردد"
2
3
4
5
6
Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Legend
| CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
Signature | Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: