## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-EL-PY-0005_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2348 |  |  | Transmital Date: 10-Sep-2023
Document Title: Area Electrical Cable Route & Section Layout |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-EL-TR-2348 |  |  | Transmital Date: 10-Sep-2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-EL-PY-0005_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | آیتمهای 1و 2و 3و 5و6 از ریپلای شیت لحاظ نشده است. بعد از نهایی سازی مدارک مرتبط مدرک ارسال گردد. |  | 1402-2294-304487 | 1402-08-02 | این مدرک بر اساس آخرین لیست کابلها و مدرک undergorund بازبینی شده و جهت مشاهده آن کارفرمای محترم ارسال می گردد.
2 | بدیهی است که مسئولیت تطابق مدارک اصلاحی با نقطه نظرات کارفرما و همچنین صحت و کفایت محتوای کلیه مدارک ارسالی مطابق شرح خدمات و استاندادرهای تصریح شده در اسناد مناقصه، استانداردهای IPS بر عهده پیمانکار بوده و نقطه نظرات کارفرما رافع مسئولیت پیمانکار نمی باشد. |  | 1402-2294-304487 | 1402-08-02 | مسئولیت مدرک یا این پیمانکار است.
3 | مدرک بدون اعمال شماره گذاری بر اساس استاندارد NISOC-E-GN-120 قابیلت انتشار در سازمان را ندارد. |  | 1402-2294-304487 | 1402-08-02 | مطابق با روال گذشته برای تمامی مدارک در همه دیسیپلینها، این مدرک شماره گذاری شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Roohizadeh | Signature |  |  |  | Clarified By: | Signature
| Date: 17-Sep-23 |  |  |  |  | Date: