## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GNRAL-PEDCO-000-PI-SP-0014 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0039 |  |  | Transmital Date: 8/9/2021
Document Title: SPECIFICATION FOR PIPE SUPPORT |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PI-TR-0039 |  |  | Transmital Date:8/9/2021
[5 empty] | CRS No: PEDCO-CRS-BK-GNRAL-PEDCO-000-PI-SP-0014_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در بند 1-2 صفحه 5 موارد زير اضاقه شود: IPS-E-GN-100 “Engineering Standard for Units” |  | BK-SUR-ENG-PIP-00-01462 | 2021-09-05 | نقطه نظر اعمال گردید
2 | ذر صفحه 6 بند 4-2 تحت عنوان استانداردهاي بين المللي اضافه شود و به استانداردهاي زير اشاره شود: MSS (MANUFACTURERS STANDARDIZATION SOCIETY) SP-69: 2002 “Pipe Hangers and Supports Selection and Application” ASTM (AMERICAN SOCIETY FOR TESTING AND MATERIALS) ASTM A 123/A123M-02 “Standard Specification for Zinc (Hot Dip Galvanized) Coatings on Iron and Steel Products.” ASTM A 653/A653M/04a “Standard Specification for Steel Sheet, Zinc Coated (Galvanized) or Zinc-Iron Alloy-Coated (Galvanized) by the Hot-Dip Process.” ASTM B696-00(2004)e1 “Standard Specification for Coatings of Cadmium Mechanically Deposited.” ASTM B766-86 “Standard Specification for Electrodeposited Coatings of Cadmium.” ASME (AMERICAN SOCIETY OF MECHANICAL ENGINEERS) ASME Section IX “Welding and Brazing Qualifications” |  | BK-SUR-ENG-PIP-00-01462 | 2021-09-05 | نقطه نظر اعمال گردید
3 | دربند 3 موارد زير اضافه بود: Contractor Person, Firm, Company or corporation with whom the company has entered in to a contract for design engineering, procurement, construction and commissioning of the project. Supplier/ Vendor Party, which manufactures or supplies equipment and services to perform the duties specified by the Contract. |  | BK-SUR-ENG-PIP-00-01462 | 2021-09-05 | نقطه نظر اعمال گردید
4 | در بند4 صفحه 6 متن زير اضافه شود: This Standard is based on International System of Units (SI) as specified in IPS-E-GN-100. |  | BK-SUR-ENG-PIP-00-01462 | 2021-09-05 | نقطه نظر اعمال گردید
5 | در بند5 صفحه 6 متن زير اضافه شود: Pipe supports shall be designed, manufactured, fabricated, inspected and/or selected for installation In accordance with ASME B31.3, MSS SP-58-2002, MSS SP-69-2002, MSS SP-89-1998, UL203- 2005, IPS-D-PI-130 and this Standard. |  | BK-SUR-ENG-PIP-00-01462 | 2021-09-05 | نقطه نظر اعمال گردید
6 | در بند6 صفحه 6 متن زير اضافه شود: Typical Spring assembly details showing the various components and spring assemblies covered by this specification shall be provided by the CONTRACTOR. Theses assemblies shall be crossreferenced on the spring/hanger Data sheets, as appropriate, to indicate to the Supplier the items required to produce complete spring/hanger support assemblies. |  | BK-SUR-ENG-PIP-00-01462 | 2021-09-05 | نقطه نظر اعمال گردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: