## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W008N-PEDCO-110-GT-RT-0001 |  |  |  |  | EPC Contractor Tr. No.:BK-HD-PEDCO-T-2512 |  |  | Transmital Date:11/26/2023
Document Title: Geotechnical Investigation Report - W008N |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-GT-T-2512 |  |  | Transmital Date:11/26/2023
[5 empty] | CRS No:NISOC-CRS-BK-W008N-PEDCO-110-GT-RT-0001_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به مكاتبات متعدد (از جمله نامه شماره 16668مورخ 22/8/1401 ) و جلسات برگزار شده قبلي و برطرف نشدن نقطه نظرات فني پتروايران، تاكيد مي گردد مسئوليت تاييد كفايت و صحت اطلاعات درج شده گزارش هاي مكانيك خاك جهت بهره گيري در طراحي و اجرا متوجه پيمانكار بوده و كليه تبعات استفاده از پارامتر ها در طراحي و اجرا متوجه پيمانكار/مشاور خواهد بود |  | BK-SUR-ENG-CIV-02-08845 | 2023-11-28 | مورد تایید است
2
3
4
5
6
Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Legend
| CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
Signature | Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: