## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PI-RT-0001_D04 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2164 |  |  | Transmital Date: 5/31/2023
Document Title: Piping Corrosion Study & Material Selection Report |  |  |  |  | PEDCO Tr. No.:BK-HD-PEDCO-T-2164 |  |  | Transmital Date: 5/31/2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PI-RT-0001_D04 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | جهت پوشش قسمت BOOT مخزن Knock Out Drum با توجه به ماند سیال Dead Leg و خورنده بودن، پیشنهاد می گردد امکان استفاده از متریال همانند سیستم پایپینگ خروجی به صورت ss316l به عنوان کلدینگ بررسی گردد. |  | 1402/2294/161209 | 1402/04/26 | احتراما این نقطه نظر طی نامه شماره BK/PEDCO/NISOC/0205/GE/LT/7683 به آن کارفرمای محترم پاسخ داده شده است و طبق نامه شماره 02/2294/255436 تاریخ 01/07/1402 دریافتی از کارفرمای محترم کامنت بر طرف شده است.
2 | موارد اصلاح شده در مدرک مطالعات خوردگی و انتخاب مواد در مدرک p&id و MFD اعمال و جهت بررسی ارسال گردد. |  | 1402/2294/161209 | 1402/04/26 | احتراما این نقطه نظر طی نامه شماره BK/PEDCO/NISOC/0205/GE/LT/7683 به آن کارفرمای محترم پاسخ داده شده است و طبق نامه شماره 02/2294/255436 تاریخ 01/07/1402 دریافتی از کارفرمای محترم کامنت بر طرف شده است.
3 | در نقاطی که از دو آلیاژ مختلف در طراحی استفاده می شود تمهیدات لازم به منظور جلوگیری از خوردگی گالوانیک مدنظر قرار گیرد. |  | 1402/2294/161209 | 1402/04/26 | احتراما این نقطه نظر طی نامه شماره BK/PEDCO/NISOC/0205/GE/LT/7683 به آن کارفرمای محترم پاسخ داده شده است و طبق نامه شماره 02/2294/255436 تاریخ 01/07/1402 دریافتی از کارفرمای محترم کامنت بر طرف شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri M.Hemmatikia | Signature |  |  |  | Clarified By: S.Faramarzpour | Signature
| Date: 06-Jun-2023 |  |  |  |  | Date: 06-Jun-2023