## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-DT-0006 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2145 |  |  | Transmital Date: 5/27/2023
Document Title: Data Sheets For Displacer Level Transmitter |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-2145 |  |  | Transmital Date: 5/27/2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-IN-DT-0006_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | صرف ملاحظه نظرات کفایت نمیکند، پیرو نامه ۳۸۵۲۳۰ مورخ ۱۴۰۱/۱۰/۱۱، ضروریست نظرات کارفرما برروی مدارک اعمال گردد. با توجه به عدم اعمال نظرات قبلی مدرک عودت میشود. |  | 1402-2294-137962 | 1402/04/10 | مدرک با توجه به تغییرات سایر مدارک پایه به روز رسانی ومطابق مذاکرات تلفنی ، از آنجا که اکثر موارد از کامنت شیت های قبلی در مدرک اعمال شده بود، این نسخه مجددا به صورت AFC ارسالگردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: