## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-IN-DG-0005 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2345 |  |  | Transmital Date: 9/5/2023
Document Title: Control System/ESD system Loop Diagram |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-2345 |  |  | Transmital Date: 9/5/2023
[5 empty] | CRS No:NISOC-CRS-BK-PPL-PEDCO-320-IN-DG-0005_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | علت حذف صفحه ۲۱ نسبت به ویراش قبل بیان گردد. |  | 1402-2294-296011 | 1402/07/26 | محتوای صفحه ۲۱ در دو نسخه اخیر در صفحه ۲۰ آورده شده است. ساختار مدرک درنسخه D01 به طور کلی تغییر کرده است لذا شماره صفحات به تبع آن تغییر یافته است.
2 | به چه علت برای سولونویید ولو ها جعبه اتصال JB در نظر گرفته نشده است. |  | 1402-2294-296011 | 1402/07/26 | مطابق مدرک تایید شده INSTRUMENT JUNCTION BOX TERMINATION DIAGRAM ، از انجا که تنها یک سیگنال برای قطع سولنویید شیر ESDV به فیلد ارسال میشودبرای آن JB دیده نشده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: 2 Oct 2023 |  |  |  |  | Date: