## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-MR-002 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2225 |  |  | Transmital Date: 6/22/2023
Document Title: PMR For Instrument Tube and Fitting |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-2225 |  |  | Transmital Date: 6/22/2023
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-IN-MR-0023_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مطابق بند 13 شرايط عمومي پيمان في مابين و با توجه به مسئوليتهاي كامل مالي/قراردادي پيمانكار, مسئوليت بروز هرگونه اشتباه و تناقض, كمبود اسناد و مدارك فني و اطلاعات تهيه شده توسط پيمانكار, اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد, به عهده پيمانكار فرعي مي باشد. |  | BK-SUR-ENG-INS-02-08047 | 2023-07-09 | ملاحظه گردید.
2 | Min Requirement ها براي ITP در مدرك آورده شود. (Monitoring/Review/witness) |  | BK-SUR-ENG-INS-02-08047 | 2023-07-09 | مطابق فرمت MRهای تایید شده پروژه، بند 6 اصلاح گردید. همچنین جزئیات ITP توسط سازنده اعلام خواهد شد.
3 | Quality Control Plan (QCP) بر اساس مدارك پروژه مشخص شود. |  | BK-SUR-ENG-INS-02-08047 | 2023-07-09 | در بند 5.1.1 و بند 6 بیان شده است همچنین با توجه به ردیف 8 جدول ضمیمه 1 ، در فایل ضمیمه قرار داده شده است.
4 | براي Trace راحت تر مدرك در يكي از ضمايم، مسئوليت هاي مربوط به Vendor و Purchaser مشخص شود. |  | BK-SUR-ENG-INS-02-08047 | 2023-07-09 | اصلاح گردید.
5 | با توجه به اينكه مدارك پيش نياز اين مدرك مانند ديتاشيت نهايي نمي باشد، MR نهايي نمي باشد. |  | BK-SUR-ENG-INS-02-08047 | 2023-07-09 | ملاحظه گردید.
6 | كلمات VENDOR و SUPPLIER در مدرك يكسان سازي شده و مطابق توضيحات بخش GENERAL DEFINITION از كلمه VENDOR استفاده گردد. |  | BK-SUR-ENG-INS-02-08047 | 2023-07-09 | اصلاح گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: