## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-AR-DW-0010 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2517 |  |  | Transmital Date:12/2/2023
Architectural Drawing For CCTV Rack Room- Binak PU |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-AR-TR-2517 |  |  | Transmital Date: 12/2/2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-AR-DW-0010_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نوت شماره یک با توجه به اینکه واحد اندازه گذاری در پلان میلیمتر است،عبارت سانتیمتر به میلیمتر اصلاح گردد. |  | 1402-2294-402332 | 1402/10/04 | اصلاح گردید.
2 | عطف به جلسه گذشته با کارشناس مربوطه، قرار شد پروفیل نبشی از جدول نعل درگاهی در شیت 4/9 حذف گردد و به جای آن از پروفیل IPE یا ناودانی استفاده شود. |  | 1402-2294-402332 | 1402/10/04 | اصلاح گردید.
3 | عرض دربها به یک متر اصلاح گردد و جزییات پروفیلهای دربها و پنجره ها نیز اضافه شود. |  | 1402-2294-402332 | 1402/10/04 | اصلاح گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: