## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-CV-PY-0005 |  |  |  |  | EPC Contractor Tr. No.:BK-HD-PEDCO-T-2096 |  |  | Transmital Date:05/13/2023
Document Title:Road, Paving And Plant Finish Grading Layout & Sections |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-CV-TR-2096 |  |  | Transmital Date:05/13/2023
[5 empty] | CRS No:NISOC-CRS-BK-GCS-PEDCO-120-CV-PY-0005_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مقتضی است این مدرک درتطابق کامل با مدرک مصوب پلات پلن با لحاظ کلیه تغییرات مترتبه آن باشد. لذا ویرایش آتی مدرک بعد از مصوب شدن مدرک پلات پلان و تغییرات وابسته بدان ارائه شود |  | 1402-2294-85325 | 1402/03/06 | نقطه نظرات کارفرمای محترم اعمال گردید.
| در دیتیل 4 شیت 10/10 مقتضی است ارتفاع کانیو طرفین جاده به اندازه 15 سانتیمتر از رقوم نهایی آسفالت بالاتر باشد.(مطابق دیتیلهای 1و2 ارائه شده در همین شیت) و درفواصلی-مثلا هر 2 متر-جهت تخلیه آب جاده به صورت دندانه ای اجرا گردد. دندانه ای بودن با یک نوت ارائه گردد. |  | 1402-2294-85325 | 1402/03/06 | نقطه نظرات کارفرمای محترم اعمال گردید.
| در دیتیل 3 شیت 10/10 آبرو طرفین جاده لحاظ گردد. |  | 1402-2294-85325 | 1402/03/06 | نقطه نظرات کارفرمای محترم اعمال گردید.
| در دیتیلهای 1 و 2 شیت 10/10 ، دندانه ای اجرا شدن دیواره آبرو بصورت نوت درج گردد. |  | 1402-2294-85325 | 1402/03/06 | نقطه نظرات کارفرمای محترم اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: