## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-DT-0016 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2438 |  |  | Transmital Date: 10/17/2023
Document Title: Process Data Sheets For Lean Glycol Storage Tank |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-2438 |  |  | Transmital Date: 10/17/2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0016_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | می بایست شماره مربوط به آخرین رویژن مدرک ارسالی به صورت صحیح درج گردد. |  | 1402-2294-467719 | 1402/11/15 | اصلاح گردید.
2 | فشار عملیاتی می بایست مطابق با اسناد پایه در نظر گرفته شود. این مهم در مدرک PID لحاظ شده است. BLANKETING VALVES SETTING: 10 mbarg- VENT VALVES SET PRESSURE: max 50 mbarg- |  | 1402-2294-467719 | 1402/11/15 | فشار BLANKETING VALVES SETTING و VENT VALVES SET PRESSURE در NOTE 9 مدرک فوق ارائه شده است. لازم به ذکر است بازه فوق در آیتم مربوط به فشار عملیاتی نیز اصلاح گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: Date: |  |  |  |  | Date: