## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-DT-0010 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2438 |  |  | Transmital Date: 10/17/2023
Document Title: Process Data Sheets For Close Drain Drum |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-2438 |  |  | Transmital Date: 10/17/2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0001_D04 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | سطوح HHLL و HLL می بایست مطابق رویژن قبل مدرک لحاظ گردد. |  | 1402-2294-467719 | 1402/11/15 | اصلاح گردید.
1 | ارتفاع مخزن V-2202 نسبت به زمین می بایست پس از نهایی سازی نوع پمپ ها نهایی گردد و در این مرحله با توجه به در جریان بودن مکاتبات تصمیم گیری فی مابین و عدم قطعیت در این خصوص، نهایی سازی مدرک مزبور در این مقطع امکانپذیر نیست( نامه شماره 340600 مورخ 1402/08/24 ) |  | 1402-2294-467719 | 1402/11/15 | پیرو توافقات صورت گرفته، به استحضار می رساند مدرک فوق به منظور ارائه اطلاعات فرآیندی و مکانیکی مخزن تحت فشار فوق در نظر گرفته شده است و ارتفاع مخزن V-2202 در مدرک فوق صرفا به منظور نمایش هماهنگی با مدرک PID ارائه شده است لذا ارتفاع مخزن فوق از زمین در مدرک PID نهایی خواد شد و از مدرک فوق حذف گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: