## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ST-DW-0067 |  |  |  |  | EPC Contractor Tr. No. : BK-HD-PEDCO-T-2539 |  |  | Transmital Date:1/30/2024
Document Title: Foundation Drawing For Utility Shelter |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0073-ST-T-2539 |  |  | Transmital Date:1/30/2024
[5 empty] | CRS No:NISOC-CRS-BK-GCS-PEDCO-120-ST-DW-0067_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 1402-2294-487410 | 1402/11/26 | نظر آن کارفرمای محترم را به این موضوع جلب می نماید که آلبوم نقشه ها و مدارک محاسباتی(دفترچه و فایل نرم افزاری) جهت بررسی و اظهار نظر برای آن مقام محترم ارسال می گردد.لذا مجددا پکیج مذکور خدمتتان ایفاد می گردد.
2 |  |  | 1402-2294-487410 | 1402/11/26 | به استحضار می رساند پس از بررسی مدرک fire proofing layout پروژه توسط واحد safety ، واحد یوتیلیتی نیاز به فایر پروفینگ ندارد که شامل شلتر هم می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: