## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ST-DW-0024 |  |  |  |  | EPC Contractor Tr. No. : BK-HD-PEDCO-T-2427 |  |  | Transmital Date:10/11/2023
Document Title: Foundation Drawing For Fire Water Storage Tanks (TK-2301A/B) |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0073-ST-T-2427 |  |  | Transmital Date:10/11/2023
[5 empty] | CRS No:PEDCO-CRS-BK-GCS-PEDCO-120-ST-DW-0024_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 02/2294/315272 | 1402/08/09 | آلبوم نقشه ها به همراه فایل و مدارک محاسباتی ارسال میگردد.
2 |  |  | 02/2294/315272 | 1402/08/09 | مدارک دیتا شیت ارسال می گردد.
3 |  |  | 02/2294/315272 | 1402/08/09 | مختصات واحد ها در ایستگاه کمپرسور گاز به صورت محلی ارائه می شود.
4 |  |  | 02/2294/315272 | 1402/08/09 | از جزئیات Specification for Storage Tank Foundation استفاده شده است
5 |  |  | 02/2294/315272 | 1402/08/09 | بتن شیب بندی لحاظ شد.
6 |  |  | 02/2294/315272 | 1402/08/09 | اصلاح گردید.
7 |  |  | 02/2294/315272 | 1402/08/09 | کامل شد.
8 |  |  | 02/2294/315272 | 1402/08/09 | با توجه به مدرک ضوابط طراحی ، لحاظ شده است
9 |  |  | 02/2294/315272 | 1402/08/09 | با توجه به ارتفاع 60 سانتیمتری نیاز به میلگرد مذکور نیست
10 |  |  | 02/2294/315272 | 1402/08/09 | در دیوار و اتصال دیوار به فونداسیون خاموت استفاده نمیگردد.
11 |  |  | 02/2294/315272 | 1402/08/09 | در قسمت نت درج شده است.
12 |  |  | 02/2294/315272 | 1402/08/09 | اضافه شد.
13 |  |  | 02/2294/315272 | 1402/08/09 | در قسمت نت 5 درج شده است
14 |  |  | 02/2294/315272 | 1402/08/09 | مشخصات اضافه گردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: