## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ST-DW-0078 |  |  |  |  | EPC Contractor Tr. No. : BK-HD-PEDCO-T-2542 |  |  | Transmital Date:1/30/2024
Document Title: Structural Drawing For CCTV Control Room- Binak DU |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0073-ST-T-2542 |  |  | Transmital Date:1/30/2024
[5 empty] | CRS No:NISOC-CRS-BK-GCS-PEDCO-120-ST-DW-0078_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 1402-2294-487404 | 1402/11/26 | بر اساس صورتجلسه مورخ 1402/08/15 ، موقعیت ساختمان های CCTV واحدهای بهره برداری و نمکزدایی و ایستگاه تقویت نهایی شده است
2 |  |  | 1402-2294-487404 | 1402/11/26 | آلبوم نقشه ها به همراه فایل و مدارک محاسباتی ارسال می گردد
3 |  |  | 1402-2294-487404 | 1402/11/26 | جزئیات مربوطه در مدرک معماری ارائه شده است
Architectural Drawing For CCTV Control Room- Binak DU/(BK-GCS-PEDCO-120-AR-DW-0009)
4 |  |  | 1402-2294-487404 | 1402/11/26 | تراز 262.00 به نقشه اضافه گردید
5 |  |  | 1402-2294-487404 | 1402/11/26 | تعداد مشخص گردید
6 |  |  | 1402-2294-487404 | 1402/11/26 | مدرک ژئوتکنیک اضافه گردید
7 |  |  | 1402-2294-487404 | 1402/11/26 | ---
8 |  |  | 1402-2294-487404 | 1402/11/26 | ---
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: