## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-MT-0003 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1130 |  |  | Transmital Date: 6/28/2022
Document Title: MTO For Instrument/F&G Junction box and Gland |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-1130 |  |  | Transmital Date: 6/28/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-IN-MT-0003_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مطابق بند 13 شرايط عمومي پيمان في مابين و با توجه به مسئوليتهاي كامل مالي/قراردادي پيمانكار, مسئوليت بروز هرگونه اشتباه و تناقض, كمبود اسناد و مدارك فني و اطلاعات تهيه شده توسط پيمانكار, اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد, به عهده پيمانكار فرعي (هيرگان) مي باشد. |  | BK-SUR-ENG-INS-01-05337 | 2022-08-02 | ملاحظه گردید.
2 | Electical protection براي JBF-A-2115~17 در نظر گرفته شود. |  | BK-SUR-ENG-INS-01-05337 | 2022-08-02 | مدرک مطابق آخرین نسخه از مدارک پیش نیاز بروزرسانی گردید و Electical protection در نظر گرفته شد.
3 | Voltage Range براي JB هاي نوع 7S مجددا مورد بازنگري قرار گيرد. |  | BK-SUR-ENG-INS-01-05337 | 2022-08-02 | مدرک اصلاح گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: