## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GNRAL-PEDCO-000-IN-SP-0007 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2039 |  |  | Transmital Date: 4/24/2023
Document Title: Specification For Pressure Safety Valves(PSV) |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-2039 |  |  | Transmital Date: 4/24/2023
[5 empty] | CRS No: PEDCO-CRS-BK-GNRAL-PEDCO-000-IN-SP-0007_D04 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مطابق بند 13 شرايط عمومي پيمان في مابين و با توجه به مسئوليتهاي كامل مالي/قراردادي پيمانكار, مسئوليت بروز هرگونه اشتباه و تناقض, كمبود اسناد و مدارك فني و اطلاعات تهيه شده توسط پيمانكار, اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد, به عهده پيمانكار فرعي (هيرگان) مي باشد. |  | BK-SUR-ENG-INS-02-07567 | 2023-05-08 | مطابق با IPS G-SF-900 بخش 13.3.1، میزان Absolute Noise Limit مجاز برای هر Work area می بایست حداکثر 115dB(A) برای کمتر از 15 دقیقه باشد. همچنین، میزان Noise مجاز برای Safety Valve ها مطابق با بخش 14.3.2 استاندارد مذکور، می بایست از میزان Absolue Noise Limit تجاوز نکند. با توجه به توضیحات فوق، عدد 85dB(A) اعلامی در بخش 7.5 مطابق با استاندارد IPS تغییر یافت.
2
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: