## QA-QC
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-MR-0009 |  |  |  |  | EPC Contractor Tr. No.:BK-HD-PEDCO-T-2261 |  |  | Transmital Date: 7/24/2023
Document Title: PMR For Centrifugal Pumps For Process Services |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0205-ME-TR-2261 |  |  | Transmital Date: 7/24/2023
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-ME-MR-0009_D02-01 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
QC comments :
1 | در بند 5.1.3، عبارت "QA Organization" به "QA/QC Organization Chart" تغيير يابد. |  | BK-SUR-ENG-MEC-01-05836 | 2022-10-04 | نقطه نظر کارفرمای محترم مد نظر قرار گرفته شده است |  |  | Closed
2 | در بند 6: -دستورالعمل انتخاب سطح بازرسي كالا و تجهيزات به شماره مدرك ICE-EID-MI-SP02-REV-01 اضافه گردد. |  | BK-SUR-ENG-MEC-01-05836 | 2022-10-04 | نقطه نظر کارفرمای محترم مد نظر قرار گرفته شده است |  |  | See Note No.5
3 | در جدول Attachment 2: -در رديف 1، عبارت "See Attachment 2" حذف گردد. - عبارت "List of Documents will be Finalized in VPIS" در نوتها اضافه گردد. |  | BK-SUR-ENG-MEC-01-05836 | 2022-10-04 | نقطه نظر کارفرمای محترم مد نظر قرار گرفته شده است |  |  | See Note No.10
4 | در بند 5.1.2 شماره مدرك بصورت صحيح''E&C-QC-SP-1" آورده شود. |  | BK-SUR-ENG-MEC-02-08233 | 2023-08-05 | Noted
5 | جهت يكسان سازي در كليه مدارك MR پروژه، نگارش توضيحات بند6 مطابق ذيل انجام گردد. |  | BK-SUR-ENG-MEC-02-08233 | 2023-08-05 | Noted
The equipment shall be inspected and tested in accordance with the Inspection &Test plan (ITP) issued by the vendor and approved by the CLIENT and EPC/EPD CONTRACTOR(GC) before the award of the order . The Inspection & Test plan (ITP ) shall be at least according to the Commodity Procurement and Manufacturing Inspection Instruction ( Docs .Nos. ICE-EID-MI-SP01-Rev01) , Inspection Level of Commodity and Equipment ( Docs .Nos. ICE-EID-MI-SP02-Rev01) and Data Sheets. The vendor shall in any case conduct all the tests required by contractual documents, specifications, codes and standards, manufacturer standard quality system and keep the relevant documentation. All required manufacturing and function test/inspection also Factory Acceptance Test /Site Acceptance Test and Quality Assurance requirements shall be considered in vendor responsibility as per project specification.
6 | لغت ''Purchaser" بايستي در قسمت General Definition تعريف گردد. |  | BK-SUR-ENG-MEC-02-08233 | 2023-08-05 | Noted
7 | جهت يكسان سازي، لغت Supplier در متون به Vendor تغيير يابد. |  | BK-SUR-ENG-MEC-02-08233 | 2023-08-05 | Noted
8 | در بند 11( Price Breakdown )شماره مدرك بصورت صحيح''E&C-QC-SP-1" آورده شود. |  | BK-SUR-ENG-MEC-02-08233 | 2023-08-05 | Noted
9 | در جدول Attachment 1(List of Reference/Applicable Documents): 1. در رديف General ، شماره مدرك بصورت صحيح E&C-QC-SP-1 ذكر گردد. 2. revison مربوط به مدرك ICE-EID-MI-SP01 ذكر گردد. |  | BK-SUR-ENG-MEC-02-08233 | 2023-08-05 | Noted
10 | در جدول Attachments 2(Vendor Documents Minimum Requirements): 1. لغت ''Deleted " از رديف اول جدول حذف گردد. 2. SAT Procedure اضافه گردد. |  | BK-SUR-ENG-MEC-02-08233 | 2023-08-05 | Noted
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: