## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-DT-0006 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1508 |  |  | Transmital Date: 10/18/2022
Document Title: Process Data Sheets For Discharge Gas K.O. Drum |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-508 |  |  | Transmital Date: 10/18/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0006_D04 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | کامنت پیشین: در سايزينگ نازل ورودی اين تفكيكگر فرض بر وجود Vane pack شده است كه در اين مدرك لحاظ نشده است. اين عدم تطابق يا در اين مدرك يا در مدرك محاسبات مي بايست تصحيح گردد. |  | BK-SUR-ENG-PCS-01-06086 | 2022-11-06 | در آخرین ویرایش مدرک Drum Sizing نازل ورودی تفکیکگر half-open pipe در نظر گرفته شده است.
2 | کامنت پیشین: در شماتيك قطره گير از تجهيزات توزيع جريان در نازل ورودي استفاده شده در حاليكه در محل مورد نظر در مدرك اين مطلب گنجانده نشده است. نام تجهیز مورد نظر Inlet Flow diverter و یا Inlet Flow distributor بوده و Internal reinforcement نمی باشد. |  | BK-SUR-ENG-PCS-01-06086 | 2022-11-06 | سوال مفهوم نمی باشد خواهشمند است توضیخات تکمیلی ارائه گردد.
3 | نقطه نظرات ارائه شده در سايزينگ ظروف، در اين مدرك نيز اعمال گردد. |  | BK-SUR-ENG-PCS-01-06086 | 2022-11-06 | اعمال گردید.
4 | ضروريست نقطه نظرات ذينفع اصلي در خصوص اين مدرك اعمال گردد. |  | BK-SUR-ENG-PCS-01-06086 | 2022-11-06 | اعمال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: