## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-PI-MT-0005 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1507 |  |  | Transmital Date: 10/17/2022
Document Title: MTO For Gaskets |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PI-TR-1507 |  |  | Transmital Date:10/17/2022
[5 empty] | CRS No:NISOC-CRS-BK-GCS-PEDCO-120-PI-MT-0005-D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مدارک MTO میبایست پس از تدوین و نهایی سازی کلیه ی مدارک مهندسی تفصیلی مربوطه تولید گردد.لذا از ان جا که تاکنون مدارک پیش گفته نهایی نشده اند، صحه گذاری و تایید این مدرک به لحاظ جنس متریال و مشخصات فنی اقلام در شرایط کنونی از سوی این امور میسر نیست.مزید تاکید اعلام میگردد از ان جا که مسئولیت طراحی تفصیلی پروژه جز تعهدات پیمانکار پروژه است و همچنین با استناد به وضعیت مدارک ارسالی(IFI) ،مسئولیت کامل عدم تطابق متریال مندرج در این مدرک صدرالذکر(مشخصات فنی و یا تعداد) در مرحله ی سفارش گذاری و خرید برعهده ی آن پیمانکار است.لذا پیگیری فرایند خرید با پذیرش تبعات پیش گفته،از سوی پیمانکار بلامانع است. در ضمن نهایی سازی مدارک پیش نیاز نیز در اولویت کار تیم مهندسی آن پیمانکار قرار گیرد. |  | 1401-2294-291189 | 1401/08/10 | مدارک پیش نیاز مانند PMS و مشخصات فنی گسکت رسال شده و هر آنچه مربوط به گسکت می باشد نهایی شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: