## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-PI-MT-0008 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1249 |  |  | Transmital Date:1401/06/20
Document Title: MTO For Insulation |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PI-TR-1249 |  |  | Transmital Date:1401/06/20
[5 empty] | CRS No:NISOC-CRS-BK-GCS-PEDCO-120-PI-MT-0008_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | از انجا که مسئولیت طراحی تفصیلی پروژه برعهده ی پیمانکار است،لذا مدارک MTO تهیه شده جهت اطلاع کارفرما محسوب میشود و میبایست براساس نتایج مدل سه بعدی و مطابق با مشخصات استانداردی مورد تایید تهیه گردد،لذا از آنجا که مبنای براورد کالا مشخص نیست،ارسال این مدارک با این شرایط یک اقدام زود هنگام به شمار می آید و قابل صحت سنجی نیست.لازم به ذکر است مسئولیت کامل بروز هرگونه تناقض(مشخصات و یا تعداد) در هر مرحله از پروژه به عهده پیمانکار است. |  | 1401-2294-220428 | 1401/06/20 | مورد تایید است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date :