## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ST-DW-0080 |  |  |  |  | EPC Contractor Tr. No. : BK-HD-PEDCO-T-2543 |  |  | Transmital Date:1/30/2024
Document Title: Structural Drawing For CCTV Rack Room- Binak PU |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-ST-TR-2543 |  |  | Transmital Date:1/30/2024
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-ST-DW-0080_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 1402-2294-487402 | 1402/11/26 | جزئیات مربوطه در مدرک معماری ارائه شده است
Architectural Drawing For CCTV Rack Room- Binak PU/(BK-GCS-PEDCO-120-AR-DW-0010)
2 |  |  | 1402-2294-487402 | 1402/11/26 | انجام شد
3 |  |  | 1402-2294-487402 | 1402/11/26 | انجام شد
4 |  |  | 1402-2294-487402 | 1402/11/26 | ---
5 |  |  | 1402-2294-487402 | 1402/11/26 | ---
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: