## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PI-MR-0011_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2556 |  |  | Transmital Date:2/5/2024
Document Title:PMR FOR PAINTING |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PI-TR-2556 |  |  | Transmital Date: 2/5/2024
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PI-MR-0011_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | ساختار کلی مدارک مورد تایید بوده ولیکن ارسال نسخه ی بعدی مدارک فوق منوط به نهایی سازی مدارک مرتبطه مهندسی و درج نسخ تایید شده(AFC)است.معذالک جهت پرهیز از مکاتبات مضاعف و تسریع در تایید مدارک فوق،نهایی سازی مدارک پیش نیاز (که در پیوست 1 مدرک اشاره شده است)در دستور کار تیم مهندسی آن پیمانکار قرار گیرد.در ضمن MTO کالا نیز جزء مدارک خرید میبایست درج گردد. همچنین برخی از کدهای مدارک در این جدول به درستی درج نشده است و با عنوان مدرک مغایرت دارد.مزید تاکید اعلام میگردد از آنجا که مسئولیت طراحی تفصیلی پروژه جزو تعهدات پیمانکار پروژه بوده و همچنین با استناد به وضعیت مدارک ارسالی(IFI)، مسئولیت کامل عدم تطابق متریال مندرج در این مدارک(مشخصات فنی و یا تعداد) در مرحله ی سفارش گذاری و خرید برعهده ی آن پیمانکار می باشد. |  | 1402/2294/487431 | 1402/11/26 | نقطه نظر کارفرمای محترم اعمال میگردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: