## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PI-MR-0006-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2550 |  |  | Transmital Date: 03/FEB/2024
Document Title: PMR For Bolt/Nuts |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PI-TR-2550 |  |  | Transmital Date: 03/FEB/2024
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PI-MR-0006_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | كلمات VENDOR و SUPPLIER در مدرك يكسان سازي شده و مطابق توضيحات بخش GENERAL DEFINITION از كلمه VENDOR استفاده گردد. |  | BK-SUR-ENG-PIP-02-09000 | 2024-02-12 | احتراما نقطه نظر کارفرمای محترم اعمال می گردد.
2 | . نگارش دو سطر اول پاراگراف توضيحات بخش 6 بصورت ذيل تكميل گردد The equipment shall be inspected and tested in accordance with the Inspection &Test plan (ITP) issued by the vendor and approved by the CLIENT and EPC/EPD CONTRACTOR before the award of the order . |  | BK-SUR-ENG-PIP-02-09000 | 2024-02-12 | احتراما نقطه نظر کارفرمای محترم اعمال می گردد.
3 | در جدول Attachment 1 عناوين مدارك آيتم هاي 9 و10 و شماره رويژن آيتم شماره 11 بصورت صحيح آورده شود . |  | BK-SUR-ENG-PIP-02-09000 | 2024-02-12 | احتراما نقطه نظر کارفرمای محترم اعمال می گردد.
4 | .در توضيحات مدرك، درج گردد PIM توسط سازنده قبل از برگزاري جلسه ITP, QCP, MPS لزوم ارائه مدارك |  | BK-SUR-ENG-PIP-02-09000 | 2024-02-12 | احتراما نقطه نظر کارفرمای محترم اعمال می گردد.
5 | بند 5.1.3 متناسب با نيازمنديهاي Nut & Bolt اصلاح گردد. |  | BK-SUR-ENG-PIP-02-09000 | 2024-02-12 | احتراما نقطه نظر کارفرمای محترم اعمال می گردد.
6 | جدول Attachment 2 متناسب با نيازمنديهاي Nut & Bolt اصلاح گردد. |  | BK-SUR-ENG-PIP-02-09000 | 2024-02-12 | احتراما نقطه نظر کارفرمای محترم اعمال می گردد.
7 | در بند 5.1.2 ، بعد از عبارت Spare part supply procedure ، شماره مدرك بصورت E&C-QC-SP-1 وارد گردد. |  | BK-SUR-ENG-PIP-02-09000 | 2024-02-12 | احتراما نقطه نظر کارفرمای محترم اعمال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri/J.Mosazadeh M. Torkaman | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date: 12-Feb-2024 |  |  |  |  | Date: 12-Feb-2024