## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PI-MR-0011-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2556 |  |  | Transmital Date: 05/FEB/2024
Document Title: PMR For Painting |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PI-TR-2556 |  |  | Transmital Date: 05/FEB/2024
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PI-MR-0011_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | استفاده گردد Vendor ازعنوان General Definition در مدرك يكسان سازي شده و مطابق توضيحات قسمت Supplierو Vendor كلمات |  | BK-SUR-ENG-PIP-02-09017 | 2024-02-17 | نقطه نظرکارفرمای محترم اعمال گردید.
2 | در قسمت General Definition ، عبارت Purchaser نيز تعريف گردد. |  | BK-SUR-ENG-PIP-02-09017 | 2024-02-17
3 | جهت يكسان سازي در كليه مدارك MR پروژه، نگارش توضيحات بند6 مطابق ذيل انجام گردد. |  | BK-SUR-ENG-PIP-02-09017 | 2024-02-17 | نقطه نظرکارفرمای محترم اعمال گردید.
The equipment shall be inspected and tested in accordance with the Inspection &Test plan (ITP) issued by the vendor and approved by the CLIENT and EPC/EPD CONTRACTOR(GC) before the award of the order . The Inspection & Test plan (ITP ) shall be at least according to the Commodity Procurement and Manufacturing Inspection Instruction ( Docs .Nos. ICE-EID-MI-SP01-Rev01) , Inspection Level of Commodity and Equipment ( Docs .Nos. ICE-EID-MI-SP02-Rev01) and Data Sheets. The vendor shall in any case conduct all the tests required by contractual documents, specifications, codes and standards, manufacturer standard quality system and keep the relevant documentation. All required manufacturing and function test/inspection also Factory Acceptance Test /Site Acceptance Test and Quality Assurance requirements shall be considered in vendor responsibility as per project specification.
4 | .در توضيحات مدرك، درج گردد PIM توسط سازنده قبل از برگزاري جلسه ITP, QCP, MPS لزوم ارائه مدرك |  | BK-SUR-ENG-PIP-02-09017 | 2024-02-17 | نقطه نظرکارفرمای محترم اعمال گردید.
5 | .عناوين مدارك آيتم هاي 6و5 و شماره رويژن آيتم شماره 7 بصورت صحيح آورده شود Attachment 1 در جدول |  | BK-SUR-ENG-PIP-02-09017 | 2024-02-17 | نقطه نظرکارفرمای محترم اعمال گردید.
6 | جدول Attachment 2 متناسب با نيازمنديهاي Painting اصلاح گردد. |  | BK-SUR-ENG-PIP-02-09017 | 2024-02-17 | نقطه نظرکارفرمای محترم اعمال گردید.
7 | نهايي شدن مدارك پيش نياز مانند MTO For Painting قبل از ارسال اين مدرك ضروري مي باشد. لذا از آنجا كه مدارك پيش نياز اين مدرك هنوز نهايي نشده است تائيد نهايي اين مدرك پس از نهايي شدن مدارك مذكور مقدور مي باشد. |  | BK-SUR-ENG-PIP-02-09017 | 2024-02-17 | نقطه نظرکارفرمای محترم اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri/J.Mosazadeh M. Torkaman | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date: 17-Feb-2024 |  |  |  |  | Date: 17-Feb-2024