## Reply Sheet
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GNRAL-PEDCO-000-CV-DW-0004 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2568 |  |  | Transmital Date: 2/6/2024
Document Title: Standard Drawing For Electrical Cable Trench |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-CV-TR-2568 |  |  | Transmital Date: 2/6/2024
[5 empty] | CRS No: NISOC-CRS-BK-GNRAL-PEDCO-000-CV-DW-0004_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در صفحه 1 از 4 ترنچ بتنی سه دهانه , رویژن مارک ویرایش قبلی حذف گردد. |  | 1402-2294-487359 | 1402/11/26 | انجام شد.
2 | در صفحه3 از 4 نوع ترنچ بتنی مشخص نیست , که ترنچ بتنی است یا خاکی . در ضمن نمایش دیواره ها و اسلب های کف و اسلب بالا اصلاح گردد. |  | 1402-2294-487359 | 1402/11/26 | این دیتیل ها برای نوع خاکی ترسیم شده است چون در عمق است ولی جنبه عمومی در محل تقاطع دارد. لذا عنوان Typical Section زیر عنوان عمومی آنها اضافه شد.
3 | در صفحه3 از 4 دیتایل های 4 و 7 نام فونداسیون فنس درج گردد. |  | 1402-2294-487359 | 1402/11/26 | انجام شد.
4 | کلیه علایم و اختصارها در قسمت راهنمای نقشه درج گردد. |  | 1402-2294-487359 | 1402/11/26 | انجام شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: