## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PI-0006 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2365 |  |  | Transmital Date: 9/13/2023
Document Title: P&ID - 1st Stage Gas Compression Suction Drums |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-2365 |  |  | Transmital Date: 9/13/2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0006_D07 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | عمومی: کلیه خطوط درین می بایست با شیب 1:100 لحاظ شود این مهم در خصوص Drain Header مورد تاکید کارفرما می باشد. |  | 1402-2294-338086 | 1402/08/23 | شیب خطوط drain در مدارک PID برابر با 1:100 در نظر گرفته شده است. در خصوص شیب خط Drain Header به استحضار می رساند، شیب خط مذکور مطابق با طراحی سایت موجود بینک در نظر گرفته شده است.
2 | عمومی: هر نوع تغییر در مدارک ارسالی می بایست به صورت نشان مارک نمایش داده شود در صورت تکرار این مورد مدرک عودت داده می شود. |  | 1402-2294-338086 | 1402/08/23 | مورد تایید است.
3 | فشار طراحی لحاظ شده در مدرک ارسالی برابر با 22barg درج گردیده است در صورتیکه فشار طراحی در نظر گرفته شده توسط سازنده کمپرسور (شرکت هوایار) با توجه به fail open بودن شیر recycle و محاسبات مربوطه به Settle Out Pressure برابر با 24.5 barg اعلام شده است، این مورد به دفعات به آگاهی آن پیمانکار رسانده شده است و در جلسه 1402/03/22 نیز نهایی و مورد تصمیم گیری قرار گرفته استکه متاسفانه تاکنون رفع نگردیده است لذا مقتضی است اشکالاتی ازین دست که ممکن است موجب خطا در بررسی مدارک خرید از سازنده نیز گردد در این مقطع با حساسیت بیشتر مرتفع گردد. |  | 1402-2294-338086 | 1402/08/23 | مدرک بر اساس آخرین اطلاعات دریافتی از سازنده کمپرسور بروز رسانی گردید. به استحضار می رساند بر اساس آخرین ویرایش مدارک سازنده فشار طراحی لحاظ شده 22 BARG می باشد.
4 | کلاس خط ورودی به V-2101 به شماره GAS-111-0026A-AN07-8"-PT می بایست از AN07 به CN07 تغییر یابد(با توجه به FAIL OPEN گردیده شیر RECYCLE) |  | 1402-2294-338086 | 1402/08/23 | اصلاح گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: