## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PI-0007 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2365 |  |  | Transmital Date: 9/13/2023
Document Title: P&ID - 1st Stage Gas Compression Compressors |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-2365 |  |  | Transmital Date: 9/13/2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0007_D07 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | عمومی: کلیه خطوط درین می بایست با شیب 1:100 لحاظ شود این مهم در خصوص Drain Header مورد تاکید کارفرما می باشد. |  | 1402-2294-338086 | 1402/08/23 | شیب خطوط drain در مدارک PID برابر با 1:100 در نظر گرفته شده است. در خصوص شیب خط Drain Header به استحضار می رساند، شیب خط مذکور مطابق با طراحی سایت موجود بینک در نظر گرفته شده است.
2 | عمومی: هر نوع تغییر در مدارک ارسالی می بایست به صورت نشان مارک نمایش داده شود در صورت تکرار این مورد مدرک عودت داده می شود. |  | 1402-2294-338086 | 1402/08/23 | مورد تایید است.
3 | با توجه به توضیحات بند قبل فشار طراحی لحاظ شده در مدرک ارسالی برابر با 22 BARG می باشد در صورتیکه فشار طراحی در نظر گرفته شده توسط سازنده کمپرسور (شرکت هوایار) برابر 24.5 BARG لحاظ شده است که ضروریست در مدرک اصلاح گردد. |  | 1402-2294-338086 | 1402/08/23 | مشخصات طراحی کمپرسور بر اساس آخرین اطلاعات شرکت هوایار بروز رسانی گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: