## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PI-0006 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2365 |  |  | Transmital Date: 9/13/2023
Document Title: P&ID - 1st Stage Gas Compression Suction Drums |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-2365 |  |  | Transmital Date: 9/13/2023
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0006_D07 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با اعمال نظرات ذیل، مدرک مورد تایید می باشد. شایان ذکر است که مطابق شرایط عمومی پیمان فی ما بین و با توجه به مسئولیتهای مالی-قراردادی پیمانکار، مسئولیت بروز هرگونه اشتباه و تناقض، کمبود اسناد و مدارک فنی و اطلاعات تهیه شده از سوی پیمانکار اعم از اینکه از سوی کارفرما تایید شده و یا نشده باشد بر عهده پیمانکار است. |  | BK-SUR-ENG-PCS-02-08512 | 2023-09-30 | مورد تایید است.
2 | با توجه به مدارک سازنده، سولونوئید شیر Spill Back، از سیستم UCP کمپرسور فرمان می گیرد در حالیکه در این نقشه از سیستم ESD فرمان می گیرد. |  | BK-SUR-ENG-PCS-02-08512 | 2023-09-30 | سیکنال از USD نشان داده شده است که سیستم ESD مربوط به پکیج میباشد.
3 | فشار طراحی سیستم بر اساس محاسبات نهایی Settle out در این نقشه و نقشه سازنده یکسان سازی گردد. |  | BK-SUR-ENG-PCS-02-08512 | 2023-09-30 | مدرک بر اساس آخرین اطلاعات دریافتی از سازنده کمپرسور بروز رسانی گردید.
4 | کلیه تغییرات منتج از داده های سازندگان، در ویرایش نهایی مدرک اصلاح گردد. |  | BK-SUR-ENG-PCS-02-08512 | 2023-09-30 | رجوع شود به بند 3 فوق
5 | سایز همه شیرها از جمله شیرهای یکطرفه و دروازه ای روی خط مایع خروجی به سمت CD، شیرهای توپی روی خط کنارگذر و Isolation شیر اطمینان درج گردد. |  | BK-SUR-ENG-PCS-02-08512 | 2023-09-30 | اصلاح گردید.
6 | ضروريست نقطه نظرات ذينفع اصلي در خصوص اين مدرك اعمال گردد. |  | BK-SUR-ENG-PCS-02-08512 | 2023-09-30 | اعمال می‌گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: