## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PI-0007 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2365 |  |  | Transmital Date: 9/13/2023
Document Title: P&ID - 1st Stage Gas Compression Compressors |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-2365 |  |  | Transmital Date: 9/13/2023
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0007_D07 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | همه موارد CRS ویرایش پیشین پاسخ داده نشده است. |  | BK-SUR-ENG-PCS-02-08512 | 2023-09-30 | اعمال گردید.
2 | نقطه نظر عمومی پیشین: به منظور Duplicate نشدن Tag تجهیزات ابزار دقیق در بسته های مختلف (کمپرسور، نم زدا، هوا، نیتروژن و....) چه تمهیدی در نظر گرفته شده است؟ |  | BK-SUR-ENG-PCS-02-08512 | 2023-09-30 | مطابق توافقات حین جلسات، برای هر پکیج حرف اول Tilte آن به شماره های ابزار دقیق اضافه خواهد شد. این مورد به صورت Note در P&ID سازنده پکیج ذکر شده است .
3 | نقطه نظر عمومی پیشین: توضیحات مرتبط با سیگنال های ورودی به UCP کمپرسورها دقیق نبوده و بر اساس مدارک سازنده نیاز به تصحیح دارد. |  | BK-SUR-ENG-PCS-02-08512 | 2023-09-30 | مطابق توافقات حین جلسات، اصلاح شد.
4 | کلیه تغییرات منتج از داده های سازندگان، در ویرایش نهایی مدرک اصلاح گردد. |  | BK-SUR-ENG-PCS-02-08512 | 2023-09-30 | مورد تایید است.
5 | سایز همه شیرها از جمله شیرهای یکطرفه روی خط خروجی واز بسته کمپرسور و نتروژن ورودی و شیر توپی روی خط کنارگذر شیر اطمینان درج گردد. |  | BK-SUR-ENG-PCS-02-08512 | 2023-09-30 | اعمال گردید.
6 | ضروريست نقطه نظرات ذينفع اصلي در خصوص اين مدرك اعمال گردد. |  | BK-SUR-ENG-PCS-02-08512 | 2023-09-30 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: