## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PI-0012 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2365 |  |  | Transmital Date: 9/13/2023
Document Title: P&ID - 2nd Stage Gas Compression Discharge Drum |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-2365 |  |  | Transmital Date: 9/13/2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0012_D07 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | عمومی: کلیه خطوط درین می بایست با شیب 1:100 لحاظ شود این مهم در خصوص Drain Header مورد تاکید کارفرما می باشد. |  | 1402-2294-338086 | 1402/08/23 | شیب خطوط drain در مدارک PID برابر با 1:100 در نظر گرفته شده است. در خصوص شیب خط Drain Header به استحضار می رساند، شیب خط مذکور مطابق با طراحی سایت موجود بینک در نظر گرفته شده است.
2 | عمومی: هر نوع تغییر در مدارک ارسالی می بایست به صورت نشان مارک نمایش داده شود در صورت تکرار این مورد مدرک عودت داده می شود. |  | 1402-2294-338086 | 1402/08/23 | مورد تایید است.
3 | در این مقطع نقطه نظر خاصی مطرح نمی باشد پیش برد گام بعدی مهندسی بلامانع می باشد. |  | 1402-2294-338086 | 1402/08/23 | مورد تایید است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: