## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PI-0013 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2366 |  |  | Transmital Date: 9/17/2023
Document Title: P&ID - Gas Compression Dehydration Package |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-2366 |  |  | Transmital Date: 9/17/2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0013_D07 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | عمومی: کلیه خطوط drain می بایست با شیب 1:100 لحاظ شود. این مهم در خصوص Drain Header مورد تاکید کارفرما می باشد. |  | 1402-2294-339892 | 1402/08/23 | شیب خطوط drain در مدارک PID برابر با 1:100 در نظر گرفته شده است. در خصوص شیب خط Drain Header به استحضار می رساند، شیب خط مذکور مطابق با طراحی سایت موجود بینک در نظر گرفته شده است.
2 | عمومی: هر نوع تغییر در مدارک ارسالی می بایست به صورت نشان مارک و با اطلاع و اجازه کارفرما در مدارک انجام شود لیکن بارها مشاهده شده است که بدون هیچ دلیل فنی و یا حتی مغایر با آن در ویرایش های بالای مدرک که توقع بر نهایی سازی مدرک است تغییراتی بدون هیچ نشانی روی می دهد که با توجه به حجم فعالیت های سازمان کارفرما ممکن است از دیده پنهان بماند، این رویه اینک موجب بی اعتمادی به فرآیند مهندسی و مدارک تایید شده گردیده و بیهوده موجب افزایش ویرایش های مهندسی و تطویل فعالیت های مربوطه می گردد، لذا ضمن تذکر جدی در این خصوص اعلام میدارد در صورت تکرار این مورد مدارک مذکور عودت داده خواهد شد و تاخییر ناشی از چنین اشتباهاتی در تاخیر پروژه ناشی از قصور پیمانکار منظور خواهد گردید. |  | 1402-2294-339892 | 1402/08/23 | مورد تایید است
3 | با اعمال کلیه نقطه نظرات از سوی کارفرما بر مدرک P&ID تولید شده از سوی سازنده منتخب مدارک مربوط به سازنده پکیج نمزدا می بایست جایگزین مدرک فوق گردد. |  | 1402-2294-339892 | 1402/08/23 | پس از نهایی شدن و دریافت اطلاعات پکیج مذکور، مدرک P&ID مطابق مدارک سازنده منتخب بروزرسانی خواهد شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date:

## Sheet3
177500