## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PI-0014 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2365 |  |  | Transmital Date: 9/13/2023
Document Title: P&ID - Lean Glycol Storage Tank |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-2365 |  |  | Transmital Date: 9/13/2023
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0014_D07 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با اعمال نظرات ذیل، مدرک مورد تایید می باشد. شایان ذکر است که مطابق شرایط عمومی پیمان فی ما بین و با توجه به مسئولیتهای مالی-قراردادی پیمانکار، مسئولیت بروز هرگونه اشتباه و تناقض، کمبود اسناد و مدارک فنی و اطلاعات تهیه شده از سوی پیمانکار اعم از اینکه از سوی کارفرما تایید شده و یا نشده باشد بر عهده پیمانکار است. |  | BK-SUR-ENG-PCS-02-08512 | 2023-09-30 | مورد تایید است.
2 | نظر پیشین: کلیه شیرهای 2 اینچ و بزرگتر از آن، به صورت فلنجی نمایش داده شود. به عنوان نمونه شیرهای 2 اینچ قبل و بعد از PRV-2161. همچنین فلنجی بودن شیرهای 1 اینچ قبل و بعد از PRV-2162 اصلاح گردد. |  | BK-SUR-ENG-PCS-02-08512 | 2023-09-30 | اعمال گردید. لازم به ذکر است سایط قبل از PRV-2161و بعد از PRV-2162 برابر با 1" در نظر گرفته شده است..
3 | نام و سایز نازل standpipe تانک (نازل پایین) نمایش داده شود. |  | BK-SUR-ENG-PCS-02-08512 | 2023-09-30 | اعمال گردید.
4 | امکان ارسال سیال از طریق مسیر Minimum Flow، بررسی گردد. |  | BK-SUR-ENG-PCS-02-08512 | 2023-09-30 | بر اساس بند 68 مدرک HAZOP STUDY اصلاح گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: