## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PI-RT-0005 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2457 |  |  | Transmital Date: 10/28/2023
Document Title: PDMS Model Review Report (90%) |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PI-TR-2457 |  |  | Transmital Date: 10/28/2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PI-RT-0005_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به عدم حضور پیمانکار در جلسه پیشین مدل چاه ها (نامه شماره 02/2294/179557 ) مقرر گردید که موارد در جلسه بررسی مدل سه بعدی GCS بررسی گردد (نامه 02/2294/285607 ) که با توجه به کمبود زمان این امر محقق نگردید لذا ضروری است برنامه ریزی جهت برگزاری جلسات فوق در دستور کار قرار گیرد. |  | 1402-2294-359488 | 1402/09/14 | احتراما با توجه به تغییرات شرح کار این پیمانکار و کاهش کاری چاه ها از قرارداد طبیعتا نیازی به برگزاری این جلسه نخواهد بود.
2 | از آنجا که نقشه های PLOT PLAN نیز به علت کمبود زمان بررسی نشده است, ضروری است این مدرک در اسرع وقت ارائه گردد. همچنین مدرک OVERALL PLOT PLAN در دستور کار قرار گیر د |  | 1402-2294-359488 | 1402/09/14 | احتراما ویرایش D05 مدرک Unit Plot Plan Drawing با شماره ترنسمیتال T-2576 تهیه و ارسال شده است.
3 |  |  | 1402-2294-359488 | 1402/09/14 | طبق مذاکره تلفنی و توافق صورت گرفته با کارشناس مکانیک کارفرما اصلی (NISOC) مقرر گردید مدرک فوق با وضعیت AFD ارسال گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: