## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-HV-CN-0002_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1814 |  |  | Transmital Date:01/23/2023
Document Title: HVAC Calculation Note For Extension of Existing Elect. Building |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0103-HV-TR-1814 |  |  | Transmital Date:01/23/2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-HV-CN-0002_D02 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در محاسبات تهویه اتاق باتری لحاظ نگردیده است.دمای اتاق مذکور باید 24 درجه سانتیگراد باشد. |  | 1401-2294-466435 | 1401/12/07 | در این فضا (که موجود میباشد) هیچگونه بار گرمایشی جدیدی اضافه نمیشود.
2 | نظر کارفرما مطابق مکاتبات پیشین (01/2294/325652) در نظر گرفتن سیستم HVAC به صورت یکپارچه می باشد. و این رویکرد همان گونه که طی مکاتبات پیشین مکرر اعلام گردیده غیر قابل تغییر می باشد، چنانچه پیمانکار در این خصوص نقطه نظری مخالف داشته باشد این موضوع از جنبه فنی خارج گردیده و می بایست از سایر مجاری پیگیری گردد. |  | 1401-2294-466435 | 1401/12/07 | مراتب در جلسه مورخ 1402/11/30 مطرح و جمع بندی گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date: 1401/12/07 |  |  |  |  | Date: