## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-HV-PY-0015 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2526 |  |  | Transmital Date: 01/01/2024
Document Title: Plumbing & Sewage Piping Layout For Extension of Existing Control Building |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-HV-TR-2526 |  |  | Transmital Date: 01/01/2024
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-HV-PY-0015_D00 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | جنس لوله های آب و فاضلاب در نقشه مشخص گردد. |  | 1402-2294-487095 | 1402/11/25 | علی رغم اشاره به جنس مصالح در مدارک پایه، جنس مصالح لوله های آب و فاضلاب در نقشه ها (General Note) ارائه گردید.
2 | مشخصات آبگرمکن در نقشه داده شود. |  | 1402-2294-487095 | 1402/11/25 | با توجه به عدم نیاز به آب گرم بهداشتی و متعاقب آن در نظر گرفته نشدن آبگرمن، نیازی به درج مشخصات آبگرمکن نمی باشد.
2 | شیب لوله های فاضلاب در نقشه قید گردد. |  | 1402-2294-487095 | 1402/11/25 | علی رغم اشاره به بازه شیب لوله های فاضلاب در مدارک پایه، شیب خطوط لوله فاضلاب در نقشه ها (General Note) ارائه گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: