## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PI-DW-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2084 |  |  | Transmital Date: 5/9/2023
Document Title: Standard Pipe Support Drawings |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PI-TR-2084 |  |  | Transmital Date: 5/9/2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PI-DW-0001_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | بخ اطلاع می رساند همانگونه که در ویرایش مدرک بیان گردید به منظور بررسی و ردیابی استانداری نقشه های مندرج در مدرک ، ضروری است مرجع استانداردی نقشه های ارایه شده در جدول مشخصات نقشه در هر صفحه مشخص گردد و درج استاندارد های کلی در بخش 3 مدرک مورد پذیرش نیست |  | 1402-2294-96753 | 1402/03/13 | احتراما مدرک STANDARD PIPE SUPPORTطبق تجربیات پیشین در شرکت مهندسی هیرگان انرژی و سایر شرکت های مشاور بزرگ ایران نظیر شرکت سازه تهیه شده است .لازم به توضیح است که این مدرک عینا در سایر پروژه های مشابه ان کارفرمای محترم نظیر پروژه نگهداشت و افزایش تولید میدان نفتی منصوری و پروژه ایستگاه تقویت فشار میدان نفتی رامشیر تهیه و به تایید ایشان رسیده است
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date :