## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PI-DW-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2084 |  |  | Transmital Date: 05/09/2023
Document Title: Standard Pipe Support Drawings |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PI-TR-2084 |  |  | Transmital Date: 05/09/2023
[5 empty] | CRS No:PEDCO-CRS-BK-GCS-PEDCO-120-PI-DW-0001_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | شماره استانداردهاي زير در بند 3.1 اضافه شود: IPS-D-PI-130 IPS-D-PI-102 NISOK GENERAL STANDARD DRAWING |  | BK-SUR-ENG-PIP-01-04777 | 2022-06-20 | احتراما NISOC GENERAL STANDARD DRAWING اضافه گردید. |  |  | STT ITEM 5
2 | در ابتداي مدرك بندي اضافه شود و INDEX ساپورتها اضافه گردد و شماره استاندارد ساپورت در INDEX و نقشه مربوطه ذكر گردد |  | BK-SUR-ENG-PIP-01-04777 | 2022-06-20 | احتراما INDEX ساپورت ها در مدرک موجود بوده و تگ ساپورت ها در نقشه ها موجود است |  |  | CLOSED
3 | نقشه استاندارد IPS-D-PI-102 به نقشه ساپورتها اضافه شود |  | BK-SUR-ENG-PIP-01-04777 | 2022-06-20 | احتراما با توجه به وضعیت انجام استرس انالیز نیازی به نقشه های بیشتر نبوده، بدیهی است در صورت نیاز به نقشه های بیشتر مدرک به روز رسانی خواهد شد. |  |  | CLOSED
4 | نقشه تمامي ساپورتها در فرمت نقشه هاي پروژه تهيه شود |  | BK-SUR-ENG-PIP-01-04777 | 2022-06-20 | احترما کلیه نقشه ها در فرمت نقشه های پروژه (GCS; A4-Portrait ) تهیه شده است. |  |  | CLOSED
5 | شماره استاندارد زير در بند 3.1 اضافه شود: IPS-D-PI-130 |  | BK-SUR-ENG-PIP-02-07640 | 5/9/2023 | احتراما اعمال گردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date :